## Slide 1
TRADING ALERTS SAAS · MIGRATION BLUEPRINT, EXPLAINED
From Monolith to
Microservices
A plain-language guide to the 9 phases (0–8) and the Track CC engineering
foundations that Claude Code will execute — and the decisions where it needs you.
Source: docs/migration-orders/ — plan v1.2 · session playbook · chain protocol v3 · executor protocol · July 2026
ONE APP
UI
OPERATION
MONEY
Notes: This deck explains the migration implementation plan in plain language: what changes, the order of the 9 phases, the cross-cutting Track CC, and your role as the human in the loop when working with Claude Code.

## Slide 2
THE BIG PICTURE
One building becomes a campus
TODAY — THE MONOLITH
One Next.js app on Vercel does everything: the web pages, all 99 APIs, cron jobs, payments, and login — plus one shared PostgreSQL database behind it.
A bug anywhere can take down everything
Payments and trading logic deploy together
Can't scale busy parts independently
TARGET — SPECIALIZED SERVICES
Vercel — Next.js 16 — UI only: pages, charts, forms
Railway — operation-service — Alerts, drawings, users, login (NestJS)
Railway — money-service — Stripe, dLocal, affiliates, payouts (NestJS)
Railway — gateway + PostgreSQL — Market-data ingest (already live) + one DB, strict roles
Contabo — EA / MT5 stacks — Unchanged — already separate
Why: independent scaling · payments isolated from product code · smaller, safer deploys · clear ownership per service
Notes: The monolith = one building where everyone works. The target = a campus of specialized buildings. 128 files are already separate services (gateway, MT5, backend-stack-c). The migration moves the 143 backend files into two new NestJS services while the UI stays on Vercel.

## Slide 3
SPEAK THE LANGUAGE
Six words you will hear constantly
1
Contract (OpenAPI)
A written promise of exactly what each API accepts and returns. New services must match it byte-for-byte — so nothing else notices the swap.
2
Strangler pattern
Don't rewrite everything at once. Replace one slice at a time while the old system keeps running, until the monolith is 'strangled' away.
3
Shadow-run
Run old and new side by side for 48h, send both the same requests, and compare answers. Only cut over when the diff is clean.
4
Cutover & rollback
Flipping a switch (env flag) so traffic uses the new service. Every cutover has a tested way to flip back instantly.
5
Flag (F1–F18)
A marked uncertainty in the plan. Claude Code must stop, investigate, and record the decision — often it needs YOUR answer.
6
Exit criteria
The checklist a phase must pass before the next begins. If it isn't met, the phase is not done — no exceptions.
Notes: These six concepts are the backbone of the whole plan. If you understand 'contract', 'strangler', 'shadow-run', 'cutover/rollback', 'flag' and 'exit criteria', you can follow every conversation with Claude Code.

## Slide 4
THE JOURNEY MAP
Nine phases, one parallel track
0
Foundations
Contracts, staging, baselines — freeze the ground truth
1
Railway PostgreSQL (WS 7)
One database, three strict access roles + pooling
2
non_market_data schema (WS 6)
Upgrade Prisma to v7.8.0, then split the data model
3
Hybrid JWT auth (WS 2)
One secure token that every service accepts
4
Backend move to NestJS (WS 5)
143 files migrate slice-by-slice (strangler)
5
Next.js 16 upgrade (WS 4)
Runs IN PARALLEL with Phase 4 — frontend plumbing
6
Frontend redesign (WS 3)
UI catches up with the new backend features
7
API client rewrite (WS 1)
Deliberately LAST — it wraps everything else
8
Decommission & verify
Delete old routes, full e2e, 30-day stability
TRACK CC — ENGINEERING FOUNDATIONS runs alongside ALL phases: environments & CI/CD, monitoring, resilience, security, backups, runbooks…
Notes: Execution order: 7 -> 6 -> 2 -> 5 -> 4 -> 3 -> 1 in workstream numbers, shown here as Phases 0-8. Phase 5 (Next.js 16) runs in parallel with Phase 4. Track CC is not a phase — it runs continuously and 'gates' several phases (a phase cannot start until its CC prerequisites are live).

## Slide 5
PHASE 0
Foundations: measure twice, cut once
1
Study the working example
railway-gateway/ is already a NestJS service on Railway — it's the template every new service copies.
2
Write the contracts
An OpenAPI spec for all 99 existing API routes. This becomes the law every new service must obey.
3
Inventory the secrets
Which service needs which keys (Stripe, dLocal, database, JWT…) — a matrix, before anything moves.
4
Record the baseline
Run every existing test and save the results. 'No worse than this' is the bar for every later phase.
5
Pin the versions
Verify Next.js 16.2.10 / NestJS 11.1.28 / Prisma 7.8.0 exist on npm and lock them (Flags F2, F19).
6
Open Track CC
Staging environment + local dev stack come alive now — later phases assume they exist.
Nothing is built or moved in Phase 0. Its whole job is making every later phase boring and predictable.
Notes: Phase 0 = preparation only. Key human inputs: confirm access to Railway/Vercel dashboards, and answer flags F1-F3 (route inventory, version pins, where the current database actually lives).

## Slide 6
PHASES 1–2 · WORKSTREAMS 7 & 6
Database first: one vault, three different keys
1
Railway PostgreSQL + access roles
money_svc key opens ONLY the 10 money tables (payments, commissions, payouts)
core_app key opens everything EXCEPT the money tables
gateway_ingest key writes ONLY market data (formalizes what already runs)
Even before services split, the DATABASE enforces who may touch what — mistakes become impossible, not just forbidden. PgBouncer (a connection 'reception desk') keeps hundreds of visitors from overwhelming it.
2
Split the data model (Prisma)
Prisma → v7.8.0 first — Upgraded as its own fully-tested step BEFORE any splitting (Flag F19) — one variable at a time.
market_data schema — The trading candles table only — already built, untouched.
non_market_data schema — Everything else: users, alerts, subscriptions, payments… — NEW build.
+ RefreshToken table — Added now because Phase 3's login system will need it.
Zero behavior change — App runs as before; first migration is a no-op baseline, never a 'create'.
You will notice nothing as a user during these phases — that is the point.
Notes: Phase 1 human input: Flag F3 — Claude Code must first find out WHERE the current database is hosted; if it's not on Railway yet, a careful move (with rehearsed backup/restore, CC-G) is added. Phase 2 starts with step 2.0: upgrading Prisma from the outdated 5-era version to 7.8.0 in isolation (Flag F19 — a two-major-version jump needing a breaking-change audit), THEN the schema split. Other Phase 2 human input: approve the model census (F4) and schema file layout (F5).

## Slide 7
PHASE 3 · WORKSTREAM 2
One wristband, every door: hybrid JWT login
You log in
Email + password (+2FA) go to the NestJS auth service
Get a token (JWT)
A signed 'wristband' with your identity, role & tier inside
Stored safely
In an httpOnly cookie — JavaScript (and attackers) can't read it
Every door opens
Each service checks the signature itself — instantly, no phone call to a central session store
Two tokens, not one
Access token lives ~15 minutes; a refresh token (stored in the database, revocable) quietly renews it. Stolen tokens die fast.
Works in all 3 directions
Server-rendered pages, the browser directly, and service-to-service calls all use the same mechanism.
Bridge first, replace later
Today's login (NextAuth) keeps working the whole time; the new system runs alongside it and takes over only at the end of Phase 4.
F6
Your call: adopt the OpenAuth library or hand-roll on @nestjs/jwt (plan recommends bridge-first).
F7
Your call: when to upgrade key management (shared secret → JWKS).
Notes: Why JWT: with several services, a session store would need to be shared by all of them (slow, fragile). A signed token lets every service verify identity locally in ~1ms. The festival-wristband analogy: issued once at the gate, checked at every stage by looking at it — no radio call to the ticket office.

## Slide 8
PHASE 4 · WORKSTREAM 5 · THE LONG MIDDLE
The big move — one reversible slice at a time
1
Build
Rebuild one slice (e.g. 'alerts') in NestJS to match its contract
2
Shadow-run
Old + new answer the same requests for 48h in parallel
3
Compare
Diff every response; investigate every mismatch
4
Flip the flag
Traffic switches to the new service — one env variable
5
Retire
Old route deleted only after the slice proves stable
⟲ Rollback at any step = flip the flag back. Every slice is reversible until it's proven.
money-service (71 files)
Follows its own pre-written blueprint: 5 slices in order — cron jobs → payout/payment webhooks → read APIs → write APIs (Stripe/dLocal) → tier-update events. Exit bar: 30 days live, error rate < 0.1%.
operation-service (72 files)
Easiest first, riskiest last: the alert engine (already nearly independent) → shared plumbing → alerts, drawings, notifications, tiers, user settings → and only at the very end, the login system cutover (retiring NextAuth).
This is the longest phase — expect many small approvals from you, one per cutover, tracked in a single cutover table.
Notes: The strangler loop is the heart of the migration. Your role: approve each flag-flip, especially slice 4 of money-service (write APIs — real payments). Never let a cutover proceed without seeing the shadow-run diff summary and knowing the rollback. CC-F rule: once a slice enters shadow-run, its old code is frozen except mirrored bugfixes.

## Slide 9
PHASES 5–6 · WORKSTREAMS 4 & 3
The frontend catches up
5
Next.js 15 → 16 upgrade (parallel with Phase 4)
Framework plumbing only — no feature changes, so it can safely run while the backend moves.
Applies your prepared optimization docs: bundle-size reduction, font optimization, streaming.
Hard gate: bundle size and page-speed must be equal or better than before. (Flag F10: fetch the official 15→16 breaking-changes guide first.)
6
Frontend redesign — close the gap
Starts with a GAP MATRIX (Flag F11): every backend capability is checked — does the UI expose it? Missing pieces become the redesign backlog.
Unifies the three separate shells (dashboard / admin / affiliate) with shared layouts and role-aware navigation from the JWT.
Built on v16 idioms, against the new services' contracts — so it's built once, correctly.
Order matters: upgrade BEFORE redesign, so new screens are never built twice.
Notes: Phase 5 touches config and framework code only, which is why it can overlap Phase 4. Phase 6 is where you'll be most involved creatively: reviewing the gap matrix and deciding which missing features matter (F11 is partly a product decision, not just a technical one).

## Slide 10
PHASES 7–8
The finish line
7
API client rewrite — deliberately last
lib/api/index.ts is the app's 'universal remote' for talking to the backend. It has been known-broken (and unused) for months — on purpose. Auth (P3), the data split (P2) and the backend move (P4) each change what 'correct' means, so fixing it early = fixing it three times.
Now it's GENERATED from the OpenAPI contracts instead of hand-written, tested against real recorded responses, and every screen switches to it. A lint rule bans stray fetch() calls forever.
8
Decommission & final verification
✓ Delete the migrated routes and transitional mirror code from the monolith
✓ Full end-to-end journey tests: signup → alert fires → notification; checkout → payout
✓ Load test the split system; verify connection pools hold under burst traffic
✓ 30-day stability window across BOTH services before declaring victory
✓ Regenerate the architecture docs so the map matches the new territory
Notes: Phase 7 honors the two deferral flags in migration-stack-analysis.md. Phase 8's 30-day window is a patience test — resist the urge to declare success early. The physical money-database split (blueprint Phase 2) is intentionally OUT of scope; it happens later only if operational triggers fire.

## Slide 11
TRACK CC — RUNS ALONGSIDE EVERY PHASE
Nine foundations that make it robust, not just done
CC-A
Environments & CI/CD
A staging twin of production + automated per-service test pipelines; contracts checked on every change, forever
CC-B
Observability
Every request carries an ID traceable across all services; dashboards & alarms before the first cutover
CC-C
Resilience
Timeouts, retries, idempotency ('safe to repeat'), and an outbox so a payment and its tier upgrade can never disagree
CC-D
API edge & security
One URL scheme with /v1 versioning decided once; rate limits on login; uniform input validation
CC-E
Redis & queues
One Redis, disciplined namespaces (op.* / money.*); each queue owned by exactly one service
CC-F
Dev workflow
Trunk + feature flags; drift-freeze: once a slice shadow-runs, its old code only gets mirrored bugfixes
CC-G
Backup, DR & runbooks
Restore REHEARSED before anything moves; per-service runbooks; stuck payouts page a human, never retry silently
CC-H
Cost & capacity
Know the Railway bill before committing; size replicas from the load test, not guesses
CC-I
Local development
One docker-compose boots the whole system on any machine — no environment archaeology
Notes: Track CC is the difference between 'the migration worked' and 'the new system is pleasant to operate'. Highest-leverage items: CC-B (tracing — debugging 3 services without it is archaeology) and CC-C (the outbox pattern protecting payment/tier consistency).

## Slide 12
TRACK CC AS GATEKEEPER
Nothing risky starts before its safety net exists
BEFORE THIS CAN HAPPEN…
…THIS MUST ALREADY BE LIVE
WHY
Moving the database (P1)
Backup restore rehearsed on a scratch copy (CC-G)
An untested backup is a hope, not a plan
First shadow-run (P4)
Staging env + contract tests (CC-A), request tracing & alarms (CC-B), drift-freeze rule (CC-F)
You can't compare old vs new if you can't observe them
First WRITE cutover (P4, money)
Idempotency + outbox decision (CC-C), rate limits live (CC-D)
Real payments: repeats and races must be harmless first
Frontend data layer (P6)
Timeout / retry / fallback policy codified (CC-C)
One slow service should dim one panel, not the whole app
Final sign-off (P8)
Runbooks complete (CC-G), cost verified under load (CC-H)
Operations, not code, is what you live with afterwards
Notes: These five gates are written into the plan (§13, 'Where Track CC gates the phases'). When Claude Code asks to start a gated step, your first question should be: 'show me that the gate requirements are live.'

## Slide 13
HOW EVERY SESSION ACTUALLY RUNS
The Development Chain Protocol — three roles
ADVISOR / PLANNER
Claude Cowork (Fable 5 / Opus)
Turns the Executor's PRE-DRAFT + the strategy docs (plan, playbook, file inventory, templates) into the authoritative DRAFT order — best mix of template sections, skeleton as minimum content. Also maintains the playbook when sessions split or shift.
AUTHORIZER
Davin (you)
Approves every DRAFT order between sessions, every cutover flag-flip, every production deploy, and the owner-level flags (F16–F18). Your approval is the only human gate — read the one page before granting it.
EXECUTOR
Claude Code (Sonnet)
CONFIRMs the approved order against code + runtime state, executes it with tests and commits, records every deviation, updates the five artifacts, then PRE-DRAFTs the next session's order.
ORDER LIFECYCLE — never skip a state
PRE-DRAFT
by Executor
DRAFT
by Advisor
APPROVED
by Davin
CONFIRMED
by Executor
EXECUTED
by Executor
Fast-path: tiny VERIFY-RETIRE checklists (cutovers, deletions) skip the Advisor — PRE-DRAFT goes straight to Davin. Chain length: always exactly one session ahead — never draft further.
Notes: Full protocol: docs/migration-orders/00-SKELETON-AND-RULES.md section 1, and the development-chain-protocol_v3.jpg diagram. The Advisor prompt is one line: 'Here's the PRE-DRAFT from session N — produce the DRAFT for session N+1 per 00-SKELETON-AND-RULES.md.'

## Slide 14
WHY PAPERWORK IS NOT OPTIONAL HERE
Documents are the only memory
Claude Code forgets everything between sessions, and the Advisor never sees its transcript. These six files ARE the project's memory — if it isn't written in them, it didn't happen.
CLAUDE.md (repo root)
The state block: current session, current order + status, waiting-on clocks, open flags. Executor updates it at EVERY session close — it's what any fresh session reads first.
EXECUTOR-PROTOCOL.md
Claude Code's rulebook: session open/execute/close lifecycle, stop-and-ask triggers, do-not-touch list, escalation rules. Effectively frozen — changing it is changing the rules of the game.
<session>.migration-order.md
One per session: the approved work plan, its Deviations (filled during execution), and the handoff. Status in the header tracks the lifecycle.
DECISION-LOG.md
Every flag resolution (F1–F19) with evidence and who approved. Your audit trail for every judgment call made across months of work.
migration-cutover-table.md
What runs where, right now: MONOLITH → BUILT → SHADOW-RUNNING → CUT-OVER → RETIRED per slice. The Executor updates it the same session anything moves.
migration-stack-analysis.md
The 653-file inventory the Advisor plans from. Executor touches affected entries whenever a session creates, moves, or deletes files.
Notes: All six live in docs/migration-orders/ except CLAUDE.md (repo root, auto-read by Claude Code every session). This is the artifacts-are-the-only-channel rule made concrete: Deviations + CLAUDE.md are mandatory in the Executor's handoff.

## Slide 15
YOUR ROLE
You are the human in the loop
1
Answer the flags
18+ numbered decisions (F1-F19) where the plan says 'not sure - check'. Some are technical (Claude Code investigates & proposes), some are YOURS alone: F16 public URL names, F17 what data staging may use, F18 how much data-loss/downtime is tolerable.
2
Approve the gates
Every DRAFT order between sessions, phase exits, every cutover flag-flip, anything touching real money. Ask for the shadow-run diff and the rollback plan every single time - make it a ritual.
3
Provide access & facts
Railway, Vercel, Stripe, dLocal, RiseWorks dashboards; where the current database lives (F3); provider webhook consoles at slice 2. Claude Code can't see what it isn't given.
4
Protect the clock
Shadow-runs need their 48 hours; both services need their 30-day stability windows. The plan fails fastest when a human rushes it.
Claude Code executes; you decide. Every flag resolution is written to the Decision Log - your audit trail.
Notes: The plan is designed for exactly this collaboration: flags mark every uncertainty, gates mark every irreversible-ish moment, and the Decision Log records what was decided and why. Your four jobs: answer flags, approve gates (including every DRAFT order), provide access, protect the timelines.

## Slide 16
WORKING TOGETHER
How to talk to Claude Code - copy these patterns
OPENING A SESSION
“Read CLAUDE.md and EXECUTOR-PROTOCOL.md. CONFIRM this session's APPROVED order vs code + runtime state. Show me what changed - don't execute until I say go.”
CLOSING A SESSION
“Wrap up per protocol: tests + results, fill Deviations, update the artifacts, then PRE-DRAFT the next order for my approval.”
BEFORE ANYTHING RISKY
“What exactly is the rollback if this fails? Show me it was verified in staging - then wait for my go.”
AFTER A SHADOW-RUN
“Show the diff summary and EVERY mismatch with your explanation. An unexplained mismatch means no cutover.”
CLAIMED DONE
“Show me: the test command, its full output, and the commit hashes. Done means I can see it.”
GUARDING SCOPE
“Quote me the order step that covers this change. If you can't, it's out of scope - backlog it.”
GOLDEN RULES: never execute a non-CONFIRMED order · one session, one goal · evidence, not confidence · no cutover without a clean shadow-run · artifacts updated before any session ends Full guide: docs/migration-orders/HOW-TO-TALK-TO-CLAUDE-CODE.md
Notes: These prompt patterns keep you firmly in control without needing deep technical knowledge. The exhaustive situational guide - including emergencies, cutover approvals, anti-patterns and a quick-reference card - is docs/migration-orders/HOW-TO-TALK-TO-CLAUDE-CODE.md.