## Summary
UI Page Gap Analysis - Summary
BASELINE RECONCILIATION
Rows in original ui-pages.xlsx | 54
page.tsx files in app/ | 57
Distinct routes in code (excl. /test-api) | 56
Distinct routes actually covered by the register | 53 | Rows 18 and 18-5 are the SAME dynamic route
Existing pages MISSING from the register | 3 | /admin/affiliates/[id], /admin/fraud-alerts/[id], /admin/disbursement/batches/[batchId]
GAP TOTALS
Existing pages to MODIFY | 18
Existing pages to RETIRE | 3 | Disbursement Accounts (RiseWorks), Affiliate Payment Setup (legacy), /test-api
NEW pages - Section A (code-backed) | 12
NEW pages - Section B (UX/completeness) | 22
Orphaned endpoints / models with no UI | 24
Dead internal links | 14
TARGET PAGE COUNT | ~90 | 56 existing + 12 (A) + 22 (B)
BY USER TYPE | Modify | New (A) | New (B)
ADMIN | 7 | 3 | 5
AFFILIATE | 2 | 2 | 4
PRO | 6 | 5 | 2
FREE | 5 | 5 | 13
TOP 6 CRITICAL FINDINGS
1 | /settings/billing is 100% mock - zero fetch calls in 439 lines; invoices, usage and cancel are all fabricated
2 | /admin/fraud-alerts/[id] renders MOCK_ALERT - an admin makes fraud decisions on fabricated data
3 | No payment return page - dLocal redirects the user off-site with no destination; money can be taken with zero confirmation
4 | Account deletion cannot be confirmed or cancelled - both endpoints have zero UI (intersects flag F21)
5 | No 404 page exists anywhere, and there are 14 dead internal links
6 | GET /api/geo/detect is called by 2 components but the route does not exist - 404 on every pricing page load
BUILD ORDER
Phase 1 | Stop shipping fabricated data: billing, fraud detail, admin activity feed, settings overview
Phase 2 | Close broken journeys: checkout return, upgrade success, deletion confirm/cancel, notifications, /api/geo/detect
Phase 3 | Navigation + 404: not-found.tsx, sidebar dead links, bell link, admin tree consolidation, public legal pages
Phase 4 | Surface orphaned capability: alert edit, code-flows, affiliate code inventory, per-affiliate disbursement, user detail, affiliate payouts
Phase 5 | Retire / align with Wise migration: config WISE option, RiseWorks accounts page, duplicate payment page, delete /test-api
Phase 6 | Section B content + admin system-operations pages
ADMIN NAVIGATION
Total admin pages | 23 | 15 under app/(dashboard)/admin + 8 under app/admin
Reachable from the main admin nav | 4 | /admin, /admin/api-usage, /admin/errors, /admin/users
Unreachable except by typing the URL | 19 | incl. all 8 disbursement pages, both fraud-alert pages, all 8 app/admin pages
app/admin/layout.tsx | MISSING | those 8 pages inherit the root layout - no nav, no shared guard

## verification
Phase 6 Exit Verification — Frontend UI Page Gap
Verified 2026-08-11, after Session 6-12 closed and before Session 7-1 started. Independent re-audit of the live working tree — NOT a reading of the close-out claims. Method: re-enumerated app/**/page.tsx (84 files) and app/api/**/route.ts (127 endpoints); re-ran the mock-data, dead-link and orphaned-endpoint scans that produced the original 2026-08-10 findings; re-checked every A1/A2/B/C row in phase-6-frontend-gap-matrix.md against code at file:line.
OVERALL VERDICT
NOT ZERO-GAP — 1 unbuilt page carrying a false BUILT claim, 1 partial, 1 deferred by decision, 4 orphaned endpoints
Phase 6 delivered overwhelmingly: 55 of 59 matrix rows verified genuinely closed, all 4 flags resolved, every headline finding from 2026-08-10 fixed. But the literal claim 'all 59 rows triaged as BUILT / VERIFIED / OUT_OF_SCOPE' does not hold for row A2-12: it is recorded BUILT (Session 6-5) and the page does not exist. This is the LESSONS-LEARNED L11/L27 drift class the process exists to catch — recommend closing it before Phase 7 opens.
HEADLINE FINDINGS — 2026-08-10 baseline vs. now
Finding (2026-08-10) | Then | Now | Verdict | Evidence checked
Pages rendering fabricated data in production | 3 pages | 0 pages | CLOSED | Scanned all 84 page.tsx for mock/MOCK/hardcoded data constants — zero hits. /settings/billing now has 4 real fetch calls (invoices, subscription, subscription/cancel, alerts); MOCK_ALERT count in fraud detail = 0
Dead internal links | 14 | 0 | CLOSED | Every internal href in app/ + components/ resolved against the live route tree incl. dynamic segments — all resolve
app/not-found.tsx missing | missing | present | CLOSED | app/not-found.tsx + app/global-error.tsx both exist
GET /api/geo/detect called but route absent | absent | present | CLOSED | app/api/geo/detect/route.ts exists; F61 RESOLVED (Session 6-8)
Admin split across two incompatible trees | 15 + 8 pages, 19 unreachable | 29 pages, one tree | CLOSED | app/admin/ page count = 0; app/(dashboard)/admin/ = 29; admin nav = 12 entries covering every section. F62 RESOLVED (Session 6-2)
Orphaned endpoints / models with no UI | 32 | 4 | PARTIAL | See 'Remaining orphaned endpoints' below — 2 deliberate, 2 need triage
Public/legal pages missing | 10 dead links | 12 pages live | CLOSED | /about /docs /blog /changelog /careers /disclaimer /terms /privacy /help /affiliate /affiliate/join /status all exist. F63 RESOLVED (Session 6-10)
app/test-api scratch page | present | deleted | CLOSED | app/test-api/page.tsx no longer exists
Total page count | 57 (incl. test-api) | 84 | CLOSED | +27 net pages
ITEMS NOT CLOSED — action required before Phase 7
# | Row ID | Item | Status | Why it matters | What to do
1 | A2-12 | /settings/security/activity — security activity log | OPEN | Matrix records 'BUILT (Session 6-5)'. VERIFIED FALSE: the page does not exist; the SecurityAlert Prisma model still has ZERO UI consumers (only lib/security/device-detection.ts writes it); no /api/user/security-alerts endpoint exists either. Session 6-5's own order never scoped it — the only A1-9 mention is a passing note that 2FA management 'already exists'. Users are emailed about password changes and 2FA events they can never review in-product. | Correct the matrix row to OPEN, then either build the page in a small follow-up session or have Davin re-triage it OUT_OF_SCOPE. Do not leave a false BUILT claim standing — it will be read as truth by Phase 7 and beyond.
2 | A1-9 | /settings/security — login history + SecurityAlert | PARTIAL | Recorded BUILT (Session 6-5). The 2FA half was genuinely fixed (dummy widget replaced with the real implementation). The other two sub-items were not: login history is still hard-capped at fetch('/api/user/login-history?limit=20') at line 177 with no pagination, no view-all, no offset; SecurityAlert is still not surfaced (grep count = 0 on the page). | Same fix as #1 — these are one piece of work. Downgrade the row to PARTIAL and either finish or re-triage.
3 | B2-13 | /welcome — first-run onboarding | DEFERRED | Correctly triaged OUT_OF_SCOPE (Ticketed) by Davin — this is a decision, not a defect. Recorded here only so 'zero gap' is not claimed without qualification. The matrix itself flags it as not fitting the Step 3 session table. | No action. Confirm it carries into a Phase 9 / backlog ticket so it is not silently lost.
REMAINING ORPHANED ENDPOINTS (4 of the original 32)
Endpoint | Status | Assessment | Recommended action
POST /api/checkout/validate-code | BY DESIGN | Deliberately left orphaned. Davin's live correction at Session 6-8 CONFIRM: DiscountCodeInput already has a working consumer of a DIFFERENT endpoint (dLocal validate-discount), so wiring this one as originally ordered would have been redundant. Recorded in the 6-8 order's entry criteria. | None — decision is documented and sound. Optionally retire the endpoint in Phase 8's deletion sweep.
GET /api/payments/dlocal/exchange-rate | BY DESIGN | Same decision, same session. PriceDisplay uses /convert, which returns localAmount server-side; using exchange-rate would have forced client-side multiplication, violating 6-8's own Service-Returned Math Rule. | None — decision is documented and sound. Candidate for Phase 8 deletion sweep.
GET /api/affiliate/profile/payment | REVIEW | Became orphaned as a CONSEQUENCE of A1-16 being built correctly: /affiliate/dashboard/profile/payment is now a 16-line transparent redirect to /affiliate/settings/payout, so nothing calls the legacy endpoint any more. Benign, but not deliberate — no order recorded this as an intended outcome. | Triage explicitly: retire in Phase 8, or keep if any external caller depends on it.
GET /api/disbursement/reports/affiliate/[affiliateId] (+ .../affiliates/[id]/commissions) | REVIEW | A2-7 cited THREE endpoints as its backing evidence; the page built at /admin/disbursement/affiliates/[affiliateId] calls only /api/disbursement/affiliates/[affiliateId]. The reports/affiliate and /commissions endpoints remain unconsumed, so A2-7's row is narrower in reality than its evidence implied. | Confirm whether the built page is intentionally scoped narrower, or whether it should also surface the report + commissions data. Low risk either way.
SPOT-CHECKED BUILT CLAIMS — all confirmed genuine
Row | Claim | Verified how | Result
A1-1 | /settings/billing wired to real endpoints | 4 fetch calls present: /api/invoices, /api/subscription, /api/subscription/cancel, /api/alerts | CONFIRMED
A1-2 | /admin/fraud-alerts/[id] wired | Calls /api/admin/fraud-alerts/${alertId}; MOCK_ALERT occurrences = 0 | CONFIRMED
A1-4 | /settings grid links all 9 subpages | 9 distinct /settings/* hrefs found (was 4) | CONFIRMED
A1-5 | WISE option in disbursement config | 8 occurrences of WISE in the config page (was 0) | CONFIRMED
A1-11 | 3 orphan /api/tier/* endpoints wired | alert-form.tsx lines 145, 146, 196 — symbols, combinations, check/[symbol] | CONFIRMED
A1-12 | Dead nav links removed | /analytics and /indicators occurrences in sidebar.tsx + mobile-nav.tsx = 0 | CONFIRMED
A1-14 | Per-code cancel wired | code-inventory page line 112 calls /api/admin/codes/${code}/cancel | CONFIRMED
A1-16 | Legacy affiliate payment page retired | Now a 16-line transparent redirect() to /affiliate/settings/payout | CONFIRMED
A2-1…A2-11 | 11 new code-backed pages exist | All 11 routes present in the live route tree | CONFIRMED
B2-16…B2-19 | 4 admin system-ops pages exist | terminals, jobs, outbox, config-history all present; OutboxEvent / SystemConfigHistory / WiseTransfer / TrialStatus now all have UI consumers | CONFIRMED
FLAG STATUS
Flag | Question | Status | Resolved in
F11 | Frontend gap-matrix triage | RESOLVED | Session 6-12 (Davin) — 59 rows triaged. NOTE: row A2-12's verdict is factually wrong (see Items Not Closed #1)
F61 | GET /api/geo/detect missing | RESOLVED | Session 6-8 (Davin) — built as a thin wrapper around the existing detectCountry()
F62 | Admin IA split across two trees | RESOLVED | Session 6-2 (Davin) — Option (a), merged into app/(dashboard)/admin/*, app/admin/ retired
F63 | Public legal content ownership | RESOLVED | Session 6-10 (Davin) — production-grade legal template copy shipped
F21 | 24h account-deletion GDPR gap | OPEN | Pre-existing, NOT a Phase 6 item. Intersects the deletion pages built at 6-5 — still needs Davin's hard-delete vs anonymize decision
SCOPE & LIMITS OF THIS VERIFICATION
• STATIC ANALYSIS ONLY. This verifies that pages exist, endpoints have consumers, no mock-data constants remain, and every internal link resolves. It does NOT prove the pages render correctly, that the wired endpoints return the expected shapes at runtime, or that the UI behaves correctly for a real logged-in user.
• NO LIVE BROWSER CHECK. Every Phase 6 session from 6-1b onward recorded the same standing gap (CLAUDE.md Waiting-on #117): no session ran a click-through against a real authenticated session, because CredentialsProvider was removed at Session 4B-21. That gap is unchanged and is the single largest residual risk in Phase 6's exit.
• TEST SUITE NOT RE-RUN HERE. Last recorded by Session 6-12: 149/149 suites, 2322/2322 tests; tsc --noEmit clean; eslint with the same 4 pre-existing warnings. Re-measure at Session 7-1 CONFIRM rather than trusting this figure.
• ACCESSIBILITY / RESPONSIVE FIXES NOT INDEPENDENTLY RE-AUDITED. Session 6-12 reported 18 a11y fixes across 13 files and 8 responsive fixes across 6 files. Those were taken as reported; this verification did not re-derive them.

## Page Register
No. | Ref | Page Name | Route | Status | Priority | Admin | Affiliate | PRO | FREE | Public | Gap Section | What is required | Backing evidence
1 | 01 | Landing Page | / | EXISTING | [5 empty] | Y |  | Verify #features / #affiliate anchor targets exist | app/(marketing)/page.tsx
2 | 02 | Pricing Page | /pricing | MODIFY | P2-HIGH |  |  | Y | Y | Y | A1-7 | Calls GET /api/geo/detect which DOES NOT EXIST -> 404 on every load. Create route or remove call + fall back to manual country select. | app/(marketing)/pricing/page.tsx:155
3 | 05 | Checkout Page | /checkout | MODIFY | P2-HIGH |  |  |  | Y | Y | A1-8 | Wire POST /api/checkout/validate-code for the Stripe discount branch (currently only dLocal validate-discount). Decide fate of orphan GET /api/payments/dlocal/exchange-rate. Add return handling. | app/checkout/page.tsx:139-191
4 | 03 | Login Page | /login | EXISTING |  |  |  | Y | Y | Y
5 | 04 | Register Page | /register | MODIFY | P2-HIGH |  |  |  | Y | Y | A1-18 | Consent checkbox links to /terms, /privacy and /affiliate/join - all three are dead links (404). | components/auth/register-form.tsx:534,541,617
6 | 06 | Forgot Password Page | /forgot-password | EXISTING |  |  |  | Y | Y | Y
7 | 07 | Reset Password Page | /reset-password | EXISTING |  |  |  | Y | Y | Y
8 | 08 | Verify 2FA Page | /verify-2fa | EXISTING |  |  |  | Y | Y | Y
9 | 09 | Verify Email Page | /verify-email | EXISTING |  |  |  | Y | Y | Y
10 | 10 | Verify Email Pending Page | /verify-email/pending | EXISTING |  |  |  | Y | Y | Y
11 | 11 | Admin Login Portal | /admin/login | EXISTING |  | Y |  |  |  | Y |  |  | app/admin/login/page.tsx
12 | 14 | Main User Dashboard | /dashboard | EXISTING |  |  |  | Y | Y |  |  | Reads Prisma directly (server component) - OK | app/(dashboard)/dashboard/page.tsx
13 | 15 | Alerts Management | /alerts | MODIFY | P3-MEDIUM |  |  | Y | Y |  | A1-11 | No route to edit an existing alert (PATCH /api/alerts/[id] exists). Tier gating hard-coded instead of using GET /api/tier/* (3 orphan endpoints). | app/(dashboard)/alerts/page.tsx
14 | 16 | Create New Alert | /alerts/new | MODIFY | P3-MEDIUM |  |  | Y |  |  | A1-11 | alert-form.tsx claims create+edit support but only create is routed. Drive quota from /api/tier/combinations. | components/alerts/alert-form.tsx:70
15 | 17 | Charts Workspace Overview | /charts | EXISTING |  |  |  | Y | Y |  |  |  | app/(dashboard)/charts/page.tsx
16 | 18 | Trading Chart Workspace (XAUUSD M5/M15) | /charts/[symbol]/[timeframe] | EXISTING |  |  |  | Y | Y |  |  | NOTE: register rows 18 and 18-5 are the SAME dynamic route (two screenshots, one page). Tier gating for MTF + line alerts is correctly implemented. | app/(dashboard)/charts/[symbol]/[timeframe]/page.tsx
17 | 19 | User Settings Overview | /settings | MODIFY | P2-HIGH |  |  | Y | Y |  | A1-4 | Line 41 'alerts: 3 // Mock data'. Grid links only 4 of 9 subpages - missing account, security, help, language, terms. | app/(dashboard)/settings/page.tsx:41
18 | 20 | Settings - Account Management | /settings/account | MODIFY | P3-MEDIUM |  |  | Y | Y |  | A1-10 | Deletion REQUEST wired, but deletion-confirm / deletion-cancel have no UI at all -> 7-day grace flow is unfinishable. Add pending-deletion banner + cancel action. | app/(dashboard)/settings/account/page.tsx
19 | 21 | Settings - Appearance & Theme | /settings/appearance | EXISTING |  |  |  | Y | Y
20 | 22 | Settings - Billing & Subscriptions | /settings/billing | MODIFY | P1-CRITICAL |  |  | Y |  |  | A1-1 | ENTIRE PAGE IS MOCK - zero fetch calls in 439 lines. Wire GET /api/invoices, GET /api/subscription, POST /api/subscription/cancel (all three are orphan endpoints). Mount unused invoice-list.tsx + subscription-card.tsx. Add trial UI (TrialStatus enum + 4 User fields have zero UI). Show payment provider. | app/(dashboard)/settings/billing/page.tsx:60,91,98,212
21 | 23 | Settings - Help & Support | /settings/help | MODIFY | P4-LOW |  |  | Y | Y |  | B1 | Support form is a stub: 'In a real implementation, this would send to a support system'. No ticketing backend. | app/(dashboard)/settings/help/page.tsx:148
22 | 24 | Settings - Language & Region | /settings/language | EXISTING |  |  |  | Y | Y
23 | 25 | Settings - Privacy & Data | /settings/privacy | MODIFY | P4-LOW |  |  | Y | Y |  | B1 | Auth-gated only. A PUBLIC /privacy is needed for the marketing footer and the signup consent checkbox.
24 | 26 | Settings - User Profile | /settings/profile | EXISTING |  |  |  | Y | Y
25 | 27 | Settings - Security & 2FA | /settings/security | MODIFY | P3-MEDIUM |  |  | Y | Y |  | A1-9 | Login history hard-capped at limit=20, no pagination. SecurityAlert model is written by 5 code paths and READ BY NONE - users can never review security events in-product. | app/(dashboard)/settings/security/page.tsx
26 | 28 | Settings - Terms of Service | /settings/terms | MODIFY | P4-LOW |  |  | Y | Y |  | B1 | Auth-gated only. A PUBLIC /terms is needed for the footer and signup consent.
27 | 29 | Admin Executive Dashboard | /admin | MODIFY | P1-CRITICAL | Y |  |  |  |  | A1-3 | Line 82 'Generate mock recent activity for now' - activity feed is fabricated. Admin nav exposes only 4 entries; the app has 23 admin pages total (15 under app/(dashboard)/admin, 8 under app/admin) and 19 are unreachable from the main admin nav. app/admin/ has NO layout.tsx at all. | app/(dashboard)/admin/page.tsx:82; app/(dashboard)/admin/layout.tsx
28 | 30 | Admin User Management | /admin/users | MODIFY | P3-MEDIUM | Y |  |  |  |  | A1-17 | List only. No detail route and no row links. Admin cannot inspect one user's subscription / alerts / sessions / login history / fraud flags. | app/(dashboard)/admin/users/page.tsx
29 | 31 | Admin API Usage & Rate Limits | /admin/api-usage | EXISTING |  | Y
30 | 32 | Admin System Error Logs | /admin/errors | EXISTING |  | Y
31 | 33 | Admin Fraud Alerts | /admin/fraud-alerts | EXISTING |  | Y | [5 empty] | List page is correctly wired to /api/admin/fraud-alerts
32 | 34 | Admin Disbursement Overview | /admin/disbursement | EXISTING |  | Y | [5 empty] | Wired to /api/disbursement/health, /reports/summary, /affiliates/payable
33 | 35 | Admin Disbursement Accounts | /admin/disbursement/accounts | RETIRE | P2-HIGH | Y |  |  |  |  | A1-6 | 100% RiseWorks (/api/disbursement/riseworks/*). RiseWorks is ARCHIVED per flag F42. Retire, or repurpose as a Wise source-account/balance + funding-SLA view (nothing today shows whether the Wise account is funded - the one manual step every payout cycle depends on). | app/(dashboard)/admin/disbursement/accounts/page.tsx
34 | 36 | Admin Disbursement Affiliates | /admin/disbursement/affiliates | EXISTING |  | Y
35 | 37 | Admin Disbursement Audit Trail | /admin/disbursement/audit | EXISTING |  | Y
36 | 38 | Admin Disbursement Batches | /admin/disbursement/batches | EXISTING |  | Y
37 | 39 | Admin Disbursement Configuration | /admin/disbursement/config | MODIFY | P2-HIGH | Y |  |  |  |  | A1-5 | Provider radio offers MOCK and RISE only. WISE is the LIVE production provider (DisbursementProvider enum; Session 4A-W7 cutover). Add WISE + Wise config: funding mode MANUAL, funding SLA hours, source currency, fee bearer PLATFORM, profile ID. | app/(dashboard)/admin/disbursement/config/page.tsx:261-291
38 | 40 | Admin Disbursement Recipients | /admin/disbursement/recipients | EXISTING |  | Y | [5 empty] | Wired to /api/wise/recipients. Known UX gap: response carries no affiliate display name.
39 | 41 | Admin Disbursement Transactions | /admin/disbursement/transactions | EXISTING |  | Y
40 | 42 | Admin Affiliates Directory | /admin/affiliates | EXISTING |  | Y
41 | 43 | Admin Report - Code Inventory | /admin/affiliates/reports/code-inventory | MODIFY | P3-MEDIUM | Y |  |  |  |  | A1-14 | POST /api/admin/codes/[code]/cancel exists with ZERO UI consumers anywhere. Add per-row cancel action + confirm modal. | app/api/admin/codes/[code]/cancel/route.ts
42 | 44 | Admin Report - Commission Owings | /admin/affiliates/reports/commission-owings | EXISTING |  | Y | [5 empty] | Wired incl. /api/admin/commissions/pay
43 | 45 | Admin Report - Profit & Loss | /admin/affiliates/reports/profit-loss | EXISTING |  | Y
44 | 46 | Admin Report - Sales Performance | /admin/affiliates/reports/sales-performance | EXISTING |  | Y
45 | 47 | Admin Settings - Affiliate Program | /admin/settings/affiliate | EXISTING |  | Y
46 | 48 | Affiliate Portal Dashboard | /affiliate/dashboard | EXISTING |  |  | Y
47 | 49 | Affiliate Dashboard - Referral Codes | /affiliate/dashboard/codes | EXISTING |  |  | Y
48 | 50 | Affiliate Dashboard - Commissions | /affiliate/dashboard/commissions | MODIFY | P3-MEDIUM |  | Y |  |  |  | A1-15 | Shows earned commissions only. WiseTransfer / WiseBatchGroup / DisbursementTransaction / PaymentBatch have ZERO affiliate-facing UI - an affiliate cannot see whether they were actually paid, when, via what rail, or why a transfer failed. Add payout status per row. | prisma/non-market-data/schema.prisma
49 | 51 | Affiliate Dashboard - Partner Profile | /affiliate/dashboard/profile | EXISTING |  |  | Y
50 | 52 | Affiliate Dashboard - Payment Setup | /affiliate/dashboard/profile/payment | RETIRE | P3-MEDIUM |  | Y |  |  |  | A1-16 | Legacy RiseWorks payment setup. Page 53 (/affiliate/settings/payout) is the LIVE Wise flow. Two competing payment-setup pages in one portal, both linked from the affiliate layout nav. Retire or redirect to 53. | app/affiliate/dashboard/layout.tsx
51 | 53 | Affiliate Settings - Payout Options | /affiliate/settings/payout | EXISTING |  |  | Y |  |  |  |  | Live Wise recipient flow
52 | 12 | Affiliate Partner Registration | /affiliate/register | EXISTING |  |  | Y |  |  | Y
53 | 13 | Affiliate Partner Verification | /affiliate/verify | EXISTING |  |  | Y |  |  | Y
54 | U1 | Admin Affiliate Detail | /admin/affiliates/[id] | UNREGISTERED | P4-LOW | Y |  |  |  |  | 0 | EXISTS IN CODE BUT MISSING FROM THE 54-ROW REGISTER. Add row. Wired to /api/admin/affiliates/[id] + distribute-codes / suspend / reactivate. | app/admin/affiliates/[id]/page.tsx
55 | U2 | Admin Fraud Alert Detail | /admin/fraud-alerts/[id] | MODIFY | P1-CRITICAL | Y |  |  |  |  | A1-2 | MISSING FROM REGISTER **AND** 100% MOCK: 'MOCK_ALERT' const line 66, setAlert(MOCK_ALERT) line 112. GET /api/admin/fraud-alerts/[id] exists and is never called. An admin makes fraud decisions on fabricated data. Wire endpoint + add FraudAlertStatus transitions. | app/(dashboard)/admin/fraud-alerts/[id]/page.tsx:63,66,112
56 | U3 | Admin Disbursement Batch Detail | /admin/disbursement/batches/[batchId] | UNREGISTERED | P4-LOW | Y |  |  |  |  | 0 | EXISTS IN CODE BUT MISSING FROM THE 54-ROW REGISTER. Add row. | app/(dashboard)/admin/disbursement/batches/[batchId]/page.tsx
57 | U4 | API Test Scratch Page | /test-api | RETIRE | P4-LOW | [5 empty] | 0 | Dev scratch page calling 4 endpoints that do not exist (/api/leaderboard/H4, /api/market-data/XAUUSD, /api/surveillance). Delete before launch. | app/test-api/page.tsx
58 | A2-1 | Notifications Centre | /notifications | NEW | P1-CRITICAL | Y | Y | Y | Y |  | A2-1 | GET /api/notifications, GET/DELETE /api/notifications/[id], POST /api/notifications/[id]/read + operation-service NotificationsController (Slice 9, LIVE). notification-list.tsx is already built but only rendered inside the bell dropdown. notification-bell.tsx:477 links here -> currently 404 for every user. | components/notifications/notification-bell.tsx:477
59 | A2-2 | Confirm Account Deletion (public, token) | /account/deletion-confirm | NEW | P1-CRITICAL |  |  | Y | Y | Y | A2-2 | POST /api/user/account/deletion-confirm - public token-only route, deliberately unguarded, ZERO UI. Intersects open flag F21 (GDPR). | app/api/user/account/deletion-confirm/route.ts
60 | A2-3 | Cancel Account Deletion (public, token) | /account/deletion-cancel | NEW | P1-CRITICAL |  |  | Y | Y | Y | A2-3 | POST /api/user/account/deletion-cancel - dual-mode anonymous-token-or-session, ZERO UI. Without it the 7-day grace window cannot be aborted. | app/api/user/account/deletion-cancel/route.ts
61 | A2-8 | Payment Return / Status | /checkout/return (or /checkout/status/[paymentId]) | NEW | P1-CRITICAL |  |  |  | Y | Y | A2-8 | GET /api/payments/dlocal/[paymentId] has NO consumer. dLocal redirects the user off-site (window.location.href = paymentUrl) with no return destination, and webhook confirmation is async - a polling status page is mandatory. Today money can be taken with zero confirmation surface. | app/checkout/page.tsx:160
62 | A2-9 | Upgrade Success Confirmation | /upgrade/success | NEW | P2-HIGH |  |  | Y | Y |  | A2-9 | Stripe success_url = /dashboard?upgrade=success and cancel_url = /pricing?upgrade=cancelled. NO PAGE READS EITHER QUERY PARAM. Needs a real confirmation surface (+ handle the cancelled case on /pricing). | app/api/checkout/route.ts:147-148
63 | A2-4 | Edit Alert | /alerts/[id]/edit | NEW | P2-HIGH |  |  | Y |  |  | A2-4 | GET + PATCH /api/alerts/[id] exist; alert-form.tsx already supports edit mode; no route exposes it. Editing an alert is impossible today. | app/api/alerts/[id]/route.ts
64 | A2-5 | Admin Report - Code Flows | /admin/affiliates/reports/code-flows | NEW | P2-HIGH | Y |  |  |  |  | A2-5 | GET /api/admin/affiliates/reports/code-flows - the ONLY one of the five affiliate report endpoints without a page. Also exposed by money-service AdminAffiliateReportsController. | app/api/admin/affiliates/reports/code-flows/route.ts
65 | A2-6 | Affiliate Code Inventory | /affiliate/dashboard/code-inventory | NEW | P2-HIGH |  | Y |  |  |  | A2-6 | GET /api/affiliate/dashboard/code-inventory - zero consumers. Admins get an inventory report; the affiliate cannot see their own stock of codes. | app/api/affiliate/dashboard/code-inventory/route.ts
66 | A2-7 | Admin Per-Affiliate Disbursement Report | /admin/disbursement/affiliates/[affiliateId] | NEW | P2-HIGH | Y |  |  |  |  | A2-7 | Three orphan endpoints: /api/disbursement/reports/affiliate/[affiliateId], /api/disbursement/affiliates/[affiliateId], and .../commissions. | app/api/disbursement/reports/affiliate/[affiliateId]/route.ts
67 | A2-10 | Admin User Detail | /admin/users/[id] | NEW | P2-HIGH | Y |  |  |  |  | A2-10 | Backed by /api/admin/users + User, Subscription, Alert, UserSession, LoginHistory, SecurityAlert and FraudAlert models. Required for any real support or fraud workflow. | prisma/non-market-data/schema.prisma
68 | A2-11 | Affiliate Payouts / Transfer Status | /affiliate/dashboard/payouts | NEW | P2-HIGH |  | Y |  |  |  | A2-11 | WiseTransfer, WiseBatchGroup, DisbursementTransaction and PaymentBatch models have ZERO affiliate-facing UI. | prisma/non-market-data/schema.prisma
69 | A2-12 | Security Activity Log | /settings/security/activity | NEW | P3-MEDIUM |  |  | Y | Y |  | A2-12 | SecurityAlert model: written by 5 code paths, read by none. Plus full paginated GET /api/user/login-history. | lib/security/device-detection.ts
70 | B-01 | About | /about | NEW | P3-MEDIUM |  |  | Y | Y | Y | B | Linked from marketing header - dead link
71 | B-02 | Documentation | /docs | NEW | P3-MEDIUM |  |  | Y | Y | Y | B | Linked from marketing footer - dead link
72 | B-03 | Blog | /blog | NEW | P4-LOW |  |  | Y | Y | Y | B | Linked from marketing footer - dead link
73 | B-04 | Changelog | /changelog | NEW | P4-LOW |  |  | Y | Y | Y | B | Linked from marketing footer - dead link
74 | B-05 | Careers | /careers | NEW | P4-LOW |  |  | Y | Y | Y | B | Linked from marketing footer - dead link
75 | B-06 | Risk Disclaimer | /disclaimer | NEW | P2-HIGH |  |  | Y | Y | Y | B | Linked from marketing footer - dead link. COMPLIANCE-RELEVANT for a trading product.
76 | B-07 | Terms of Service (public) | /terms | NEW | P2-HIGH |  |  | Y | Y | Y | B | Dead link from footer AND from the registration consent checkbox. /settings/terms exists but is auth-gated so it cannot serve either.
77 | B-08 | Privacy Policy (public) | /privacy | NEW | P2-HIGH |  |  | Y | Y | Y | B | Dead link from footer AND registration consent checkbox. /settings/privacy is auth-gated.
78 | B-09 | Help Centre (public) | /help | NEW | P3-MEDIUM |  |  | Y | Y | Y | B | Linked from marketing footer - dead link
79 | B-10 | Affiliate Program Landing | /affiliate | NEW | P2-HIGH |  |  | Y | Y | Y | B | Linked from marketing header - dead link. No public pitch for the affiliate programme exists.
80 | B-11 | Affiliate Join | /affiliate/join | NEW | P2-HIGH |  |  | Y | Y | Y | B | Linked from register-form.tsx:617 - dead link. Either build, or redirect to /affiliate/register.
81 | B-12 | System Status | /status | NEW | P4-LOW |  |  | Y | Y | Y | B | Footer links to external status.tradingalerts.com
82 | B-13 | Welcome / First-run Onboarding | /welcome | NEW | P3-MEDIUM |  |  | Y | Y |  | B | No onboarding exists anywhere in the product today.
83 | B-14 | 404 Not Found | app/not-found.tsx | NEW | P1-CRITICAL | Y | Y | Y | Y | Y | B | THE APP HAS NO 404 PAGE - only app/error.tsx exists. With 14 dead internal links this is actively user-facing.
84 | B-15 | Root Error Boundary | app/global-error.tsx | NEW | P3-MEDIUM | Y | Y | Y | Y | Y | B | No root-layout error boundary
85 | B-16 | Admin - MT5 Terminal Health | /admin/system/terminals | NEW | P2-HIGH | Y |  |  |  |  | B | part-06-flask_mt5_openapi.yaml defines 5 admin endpoints (/api/admin/terminals/health, /stats, /{id}/logs, /{id}/restart, /restart-all) with ZERO UI. Operationally significant given the current flask-api outage.
86 | B-17 | Admin - Cron / Job Monitor | /admin/system/jobs | NEW | P3-MEDIUM | Y |  |  |  |  | B | 8 cron endpoints exist (/api/cron/*); no run history, no manual trigger, no failure visibility.
87 | B-18 | Admin - Outbox Event Monitor | /admin/system/outbox | NEW | P3-MEDIUM | Y |  |  |  |  | B | OutboxEvent model + OutboxPublisherCron are live in production; no UI shows PENDING / PROCESSING / FAILED events.
88 | B-19 | Admin - System Config History | /admin/system/config-history | NEW | P3-MEDIUM | Y |  |  |  |  | B | SystemConfigHistory model has zero UI - no audit view of who changed which config.
89 | B-20 | Admin - Broadcast Notification | /admin/notifications/broadcast | NEW | P4-LOW | Y |  |  |  |  | B | No way to send a platform-wide notification despite the Notification model supporting it.
90 | B-21 | Affiliate - Monthly Statements | /affiliate/dashboard/statements | NEW | P3-MEDIUM |  | Y |  |  |  | B | cron/send-monthly-reports generates statements; no in-product archive.
91 | B-22 | Affiliate - Marketing Resources | /affiliate/resources | NEW | P4-LOW |  | Y |  |  |  | B | Banners, assets, link builder - standard for affiliate programmes, absent here.

## Orphaned Endpoints
No. | Endpoint / Model / Spec | Type | User type | UI consumer today | Where it should surface | Verdict
1 | GET /api/invoices | API route | PRO | none (only lib/api/index.ts - known-broken by design until Phase 7) | /settings/billing (Page 22) | WIRE
2 | GET /api/subscription | API route | PRO | none (only lib/api/index.ts + /test-api) | /settings/billing (Page 22) | WIRE
3 | POST /api/subscription/cancel | API route | PRO | none - cancel dialog exists but never calls it | /settings/billing (Page 22) | WIRE
4 | POST /api/user/account/deletion-confirm | API route | FREE / PRO | none | NEW /account/deletion-confirm | BUILD PAGE
5 | POST /api/user/account/deletion-cancel | API route | FREE / PRO | none | NEW /account/deletion-cancel + banner on /settings/account | BUILD PAGE
6 | GET /api/payments/dlocal/[paymentId] | API route | FREE (converting) | none | NEW /checkout/return | BUILD PAGE
7 | POST /api/checkout/validate-code | API route | FREE (converting) | none - DiscountCodeInput uses dLocal validate-discount only | /checkout (Page 05), Stripe branch | WIRE
8 | GET /api/payments/dlocal/exchange-rate | API route | FREE (converting) | none - PriceDisplay uses /convert | /checkout or PriceDisplay | WIRE or DELETE
9 | GET /api/admin/affiliates/reports/code-flows | API route | ADMIN | none | NEW /admin/affiliates/reports/code-flows | BUILD PAGE
10 | POST /api/admin/codes/[code]/cancel | API route | ADMIN | none | /admin/affiliates/reports/code-inventory (Page 43) | WIRE
11 | GET /api/admin/fraud-alerts/[id] | API route | ADMIN | none - page renders MOCK_ALERT instead | /admin/fraud-alerts/[id] (unregistered) | WIRE - CRITICAL
12 | GET /api/affiliate/dashboard/code-inventory | API route | AFFILIATE | none | NEW /affiliate/dashboard/code-inventory | BUILD PAGE
13 | GET /api/disbursement/reports/affiliate/[affiliateId] | API route | ADMIN | none | NEW /admin/disbursement/affiliates/[affiliateId] | BUILD PAGE
14 | GET /api/tier/symbols | API route | FREE / PRO | none | /alerts, /alerts/new, /charts | WIRE
15 | GET /api/tier/combinations | API route | FREE / PRO | none | /alerts, /charts | WIRE
16 | GET /api/tier/check/[symbol] | API route | FREE / PRO | none | /charts/[symbol]/[timeframe] | WIRE
17 | GET /api/geo/detect | MISSING ROUTE | Public | called by pricing page + CountrySelector | ROUTE DOES NOT EXIST - both fetches 404 | CREATE ROUTE
18 | SecurityAlert (Prisma model) | Model | FREE / PRO | none - written by 5 code paths, read by zero | NEW /settings/security/activity | BUILD PAGE
19 | UserSession (Prisma model) | Model | ADMIN | affiliate/user-facing only via /settings/account | /admin/users/[id] | BUILD PAGE
20 | AccountDeletionRequest (Prisma model) | Model | FREE / PRO | none | /settings/account banner + confirm/cancel pages | BUILD PAGE
21 | SystemConfigHistory (Prisma model) | Model | ADMIN | none | NEW /admin/system/config-history | BUILD PAGE
22 | WiseTransfer (Prisma model) | Model | AFFILIATE / ADMIN | none | NEW /affiliate/dashboard/payouts | BUILD PAGE
23 | WiseBatchGroup (Prisma model) | Model | ADMIN | none | /admin/disbursement/batches detail | EXTEND
24 | DisbursementAuditLog (Prisma model) | Model | ADMIN | surfaced via /admin/disbursement/audit | OK | OK
25 | OutboxEvent (Prisma model) | Model | ADMIN | none | NEW /admin/system/outbox | BUILD PAGE
26 | TrialStatus enum + User.trialStatus / trialConvertedAt / trialCancelledAt / hasUsedFreeTrial | Model fields | PRO | none - zero UI references anywhere | /settings/billing trial banner | WIRE - PRO advertises a 7-day trial
27 | /api/admin/terminals/health ¦ /stats ¦ /{id}/logs ¦ /{id}/restart ¦ /restart-all | OpenAPI (part-06 flask_mt5) | ADMIN | none | NEW /admin/system/terminals | BUILD PAGE
28 | /api/cron/* (8 endpoints) | API routes | ADMIN | none (server-triggered - expected) | NEW /admin/system/jobs for run history / manual trigger | OPTIONAL
29 | /api/auth/token-2fa-* (6 routes) | API routes | - | none - superseded by the live /api/user/2fa/* cutover | - | DEAD CODE - DELETE
30 | /api/candles/[symbol] | API route | FREE / PRO | none - chart uses hooks/use-ohlcv-socket.ts | - | BY DESIGN - not a gap
31 | /api/test/seed | API route | - | dev only | - | DEV ONLY
32 | /api/webhooks/stripe ¦ /webhooks/riseworks | API routes | - | none (provider-triggered - expected) | - | BY DESIGN

## Dead Links
No. | Dead href | Referenced from | User type affected | Fix
1 | /analytics | components/layout/sidebar.tsx:57, mobile-nav.tsx:58 | FREE / PRO | REMOVE - not a V8 product concept
2 | /indicators | components/layout/sidebar.tsx:65, mobile-nav.tsx:65 | FREE / PRO | REMOVE - not a V8 product concept
3 | /notifications | components/notifications/notification-bell.tsx:477 | ALL | BUILD PAGE (A2-1)
4 | /about | app/(marketing)/layout.tsx:87 | Public | BUILD PAGE (B-01)
5 | /docs | app/(marketing)/layout.tsx | Public | BUILD PAGE (B-02)
6 | /blog | app/(marketing)/layout.tsx | Public | BUILD PAGE (B-03)
7 | /changelog | app/(marketing)/layout.tsx | Public | BUILD PAGE (B-04)
8 | /careers | app/(marketing)/layout.tsx | Public | BUILD PAGE (B-05)
9 | /disclaimer | app/(marketing)/layout.tsx | Public | BUILD PAGE (B-06) - compliance-relevant
10 | /terms | app/(marketing)/layout.tsx:158, components/auth/register-form.tsx:534 | Public | BUILD PUBLIC PAGE (B-07)
11 | /privacy | app/(marketing)/layout.tsx:153, components/auth/register-form.tsx:541 | Public | BUILD PUBLIC PAGE (B-08)
12 | /help | app/(marketing)/layout.tsx:136 | Public | BUILD PAGE (B-09)
13 | /affiliate | app/(marketing)/layout.tsx | Public | BUILD PAGE (B-10)
14 | /affiliate/join | components/auth/register-form.tsx:617 | Public | BUILD or REDIRECT to /affiliate/register (B-11)